## QA activities
Team | Dates | Description | Status
[MQA][AQA] | [July 6 – July 31] | TLS R1 2026 Trillium Bugfest testing | in progress
[Locate QA] | [TBD] | [Locate QA] Trillium Integrated Environment Testing | todo
[MQA][AQA] | [July 24 – July 31] | R1 2025 Sunflower Critical Service Patch #9 | in progress
[Locate QA] | [TBD] | LOCATE Compatibility Testing with MSK 4.1.x | todo
[AQA] | [TBD] | R1 2025 Sunflower OpenSearch 3.5 | todo
[MQA][AQA] | [TBD] | Multi-Version Support (Trillium) | todo
[AQA] | [TBD] | R1 2026 Trillium MSK 4.1.x | todo
[MQA] | [TBD] | Data Anonymization | todo
[MQA][AQA] | [Aug 24 – Aug 27] | R1 2026 Trillium – Michigan | todo
[MQA][AQA] | [Sep 1 – Sep 21] | R1 2026 Trillium – MOBIUS | todo
[MQA][AQA] | [Sep 9 – Sep 15] | R1 2026 Trillium – Cornell | todo
[AQA] | [TBD] | R1 2026 Trillium OpenSearch 3.5 | todo
[TBD] | [TBD] | FOLIO-460 Brute Force Detection by Eureka | todo
[MQA][AQA] | [Oct 6 – Oct 22] | R1 2026 Trillium CSP#1 | todo
[TBD] | [TBD] | Baseline Image Testing | todo
[TBD] | [TBD] | R2 2026 Umbrellaleaf Sprint Scope Testing | todo

## Summary
Summary | TLS LOC Trillium: Testing is ongoing with an 87% pass rate. Due to minor delays from unplanned team activities, the target completion date has been rescheduled to July 31. As of July 23, we have 22 newly opened defects. Teams, please review and triage these to identify any release blockers. Sunflower CSP#9: Testing is currently blocked pending environment readiness and deployment of the latest changes, specifically awaiting the Keycloak fix (EUREKASUP-168). Sprint 246: Automated tests are running, while manual testing is temporarily on hold due to ongoing release activities.
Fixed issues | created >= "2026-07-06" AND issuetype = Bug AND created <= "2026-08-08" AND labels = TrilliumBF AND status = Closed ORDER BY priority DESC, created DESC

## Sprint by sprint
Date | Total automated | Automated per week | Total manual | Sprint summary | Sprint automated | Sprint manual | Sprint
02.06 | 2841 | 0
12.06 | 2852 | 11
18.06 | 2864 | 12
26.06 | 2886 | 22
03.07 | 6182 | 456 | 3959
10.07 | 2986 | 63 | 5398 | 131 | 3160 | 5407 | 219
17.07 | 3071 | 85 | 5421
24.07 | 6257 | 8 | 3898
31.07 | 3239 | 79 | 5332
07.08 | 3363 | 124 | 5345 | 168 | 3363 | 5345 | 221
14.08 | 3459 | 96 | 5241
21.08 | 3545 | 86 | 5131 | 220 | 3545 | 5131 | 222
28.08 | 3606 | 61 | 5105
04.09 | 3690 | 84 | 5185 | 147 | 3690 | 5185 | 223
11.09 | 3767 | 77 | 5108
18.09 | 3839 | 72 | 5048 | 161 | 3839 | 5048 | 224
25.09 | 3921 | 82 | 5024 |  |  |  | 225
01.10 | 3936 | 15 | 4949 | 159 | 3936 | 4949 | 226
08.10 | 3952 | 16 | 4957 |  | 4029 | 4894
15.10 | 4029 | 77 | 4894 | 31 | 4181 | 4775 | 227
22.10 | 4128 | 99 | 4802
29.10 | 4181 | 53 | 4775 | 176 | 4246 | 4665 | 228
04.11 | 4246 | 65 | 4710
12.11 | 4310 | 64 | 4659 | 118 | 4374 | 4606 | 229
19.11 | 4374 | 64 | 4606
26.11 | 4395 | 21 | 4576 | 128 | 4474 | 4456 | 230
03.12 | 4474 | 79 | 4456
10.12 | 4538 | 64 | 4377 | 100 | 4612 | 4307 | 231
17.12 | 4612 | 74 | 4307
04.02 | 4803 |  | 4125 | 138 | 4803 | 4125 | 234
12.02 | 4853 | 50 | 4083
19.02 | 4908 | 55 | 4048 | 105 | 4908 | 4048 | 235
25.02 | 4954 | 46 | 4015
04.03 | 4970 | 16 | 4008 | 62 | 4970 | 4008 | 236
12.03 | 4982 | 12 | 4029
19.03 | 5039 | 57 | 4020 | 69 | 5039 | 4020 | 237
25.03 | 5071 | 32 | 3998
02.04 | 5124 | 53 | 3897 | 85 | 5124 | 3897 | 238
09.04 | 5176 | 52 | 3884
16.04 | 5230 | 54 | 3851 | 106 | 5230 | 3851 | 239
23.04 | 5305 | 75 | 3806
30.04 | 5355 | 50 | 3779 | 125 | 5355 | 3779 | 240
07.05 | 5427 | 72 | 3721
14.05 | 5493 | 66 | 3652 | 138 | 5493 | 3652 | 241
21.05 | 5516 | 23 | 3615
28.05 | 5543 | 27 | 3569 | 50 | 5543 | 3569 | 242
04.06 | 5550 | 7 | 3564
11.06 | 5633 | 83 | 3479 | 90 | 5633 | 3479 | 243
18.06 | 5688 | 55 | 3433
25.06 | 5726 | 38 | 3440 | 93 | 5726 | 3440 | 244
07.07 | 6163 | 437 | 3981
08.07 | 6192 | 29 | 3968 | 466 | 6192 | 3968 | 245
09.07 | 6195 | 3 | 3966
14.07 | 6218 | 23 | 3942 | 26 | 6218 | 3942 | 246
15.07 | 6219 | 1 | 3941
16.07 | 6206 | -13 | 3954 | -12 | 6206 | 3954 | 246
20.07 | 6230 | 24 | 3927
21.07 | 6230 | 0 | 3927 | 24 | 6230 | 3927 | 246
22.07 | 6249 | 19 | 3908
23.07 | 6249 | 0 | 3908 | 19 | 6249 | 3908 | 246

## Team coverage
as of 24.07
Team | Smoke A | Smoke M | Critical Path A | Critical Path M | Extended A | Extended M | Backend A | Backend M | Edge Cases A | Edge Cases M | Total A | Total M | Coverage %
Bienenvolk | 2 | 15 | 0 | 3 | 14 | 271 | 0 | 0 | 0 | 0 | 16 | 289 | 5.25
Citation | 21 | 51 | 98 | 72 | 95 | 16 | 0 | 0 | 2 | 2 | 216 | 141 | 60.5
Corsair | 35 | 0 | 170 | 36 | 81 | 38 | 0 | 0 | 0 | 0 | 286 | 74 | 79.44
Eureka | 27 | 6 | 69 | 21 | 13 | 2 | 1 | 1 | 0 | 1 | 110 | 31 | 78.01
Firebird | 172 | 5 | 440 | 41 | 461 | 141 | 1 | 5 | 0 | 14 | 1074 | 206 | 83.91
Folijet | 38 | 1 | 207 | 25 | 453 | 291 | 0 | 0 | 0 | 113 | 698 | 430 | 61.88
K-Int | 3 | 10 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 20
MOL | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 7 | 0 | 82 | 0
Reporting | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
Spitfire | 52 | 1 | 807 | 160 | 1510 | 393 | 5 | 8 | 0 | 1 | 2374 | 563 | 80.83
Thunderjet | 46 | 3 | 439 | 468 | 431 | 535 | 0 | 3 | 31 | 136 | 947 | 1145 | 45.27
Vega | 31 | 6 | 75 | 70 | 182 | 414 | 0 | 4 | 1 | 2 | 289 | 496 | 36.82
Volaris | 35 | 10 | 92 | 128 | 107 | 232 | 5 | 20 | 5 | 31 | 244 | 421 | 36.69

## Cypress & Karate progress
Sprint | Passed | Blocked | Untested | Retest | Failed | Unassigned | Claimed | Deferred | Deferred Hot Fix | Not Applicable | Sprint | Passed | Blocked | Untested | Retest | Failed | Unassigned | Claimed | Deferred | Deferred Hot Fix | Not Applicable | Sprint | P1 | P2 | P3 | P4 | TBD
Sprint 210 | 146 | 5 | 15 | 2 | 10 | 0 | 19 | 15 | 0 | 0 | Sprint 210 | 1790 | 0 | 397 | 14 | 551 | 0 | 0 | 0 | 0 | 10 | Sprint 210 | 1 | 14 | 18 | 5 | 5
Sprint 211 | 242 | 6 | 35 | 5 | 14 | 0 | 33 | 7 | 0 | 0 | Sprint 211 | 961 | 0 | 335 | 168 | 1332 | 0 | 0 | 0 | 0 | 0 | Sprint 211 | 1 | 2 | 2 | 0 | 1
Sprint 212 | 280 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 3 | Sprint 212 | 2548 | 0 | 6 | 6 | 219 | 0 | 0 | 7 | 0 | 8 | Sprint 212 | 0 | 8 | 13 | 3 | 4
Sprint 217 | 163 | 4 | 0 | 0 | 4 | 0 | 1 | 1 | 0 | 0 | Sprint 217 | 2443 | 0 | 41 | 9 | 341 | 0 | 0 | 0 | 0 | 0 | Sprint 217 | 0 | 0 | 5 | 0 | 2
Sprint 218 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint 218 | 2459 | 1 | 10 | 9 | 355 | 0 | 0 | 0 | 0 | 0 | Sprint 218 | 0 | 0 | 0 | 0 | 0
Sprint 219 | 88 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | Sprint 219 | 2194 | 8 | 111 | 21 | 500 | 0 | 0 | 0 | 0 | 0 | Sprint 219 | 0 | 2 | 3 | 0 | 0
Sprint 220 | 75 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 1 | Sprint 220 | 2661 | 1 | 27 | 1 | 280 | 0 | 0 | 0 | 0 | 0 | Sprint 220 | 0 | 2 | 0 | 0 | 2
Sprint 221 | 94 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Sprint 221 | 2321 | 0 | 56 | 56 | 542 | 0 | 0 | 0 | 0 | 0 | Sprint 221 | 0 | 1 | 7 | 2 | 3
Sprint 222 | 109 | 0 | 0 | 0 | 27 | 0 | 0 | 8 | 0 | 0 | Sprint 222 | 2868 | 1 | 4 | 0 | 40 | 0 | 0 | 32 | 0 | 27 | Sprint 222 | 0 | 1 | 17 | 1 | 1
Sprint 223 | 32 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint 223 | 3084 | 2 | 11 | 0 | 388 | 0 | 0 | 17 | 0 | 13 | Sprint 223 | 0 | 0 | 9 | 4 | 1
Sprint 224 | 86 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | Sprint 224 | 2604 | 1 | 69 | 28 | 805 | 0 | 0 | 0 | 0 | 0 | Sprint 224 | 0 | 1 | 2 | 0 | 0
Sprint 225 | 143 | 0 | 10 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Sprint 225 | 3103 | 1 | 56 | 2 | 324 | 0 | 0 | 0 | 0 | 0 | Sprint 225 | 0 | 2 | 1 | 0 | 0
Sprint 227 | 158 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Sprint 227 | 3522 | 2 | 70 | 4 | 388 | 0 | 0 | 9 | 0 | 1 | Sprint 227 | 0 | 3 | 5 | 0 | 2
Sprint 228 | 161 | 1 | 5 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | Sprint 228 | 2603 | 0 | 799 | 27 | 755 | 0 | 0 | 6 | 0 | 0 | Sprint 228 | 0 | 2 | 3 | 0 | 0
Sprint 229 | 152 | 2 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | Sprint 229 | 2851 | 0 | 1069 | 11 | 351 | 0 | 0 | 25 | 0 | 0 | Sprint 229 | 0 | 0 | 0 | 1 | 5
Sprint 230 | 137 | 1 | 12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Sprint 230 | 3985 | 1 | 26 | 12 | 360 | 0 | 0 | 5 | 1 | 0 | Sprint 230 | 0 | 2 | 2 | 0 | 0
Sprint 231 | 59 | 2 | 10 | 2 | 4 | 0 | 0 | 2 | 0 | 0 | Sprint 231 | 1977 | 0 | 1374 | 3 | 203 | 0 | 0 | 0 | 0 | 0 | Sprint 231 | 0 | 0 | 1 | 0 | 0
Sprint 235 | 93 | 2 | 158 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | Sprint 235 | 4298 | 2 | 40 | 1 | 533 | 0 | 0 | 0 | 0 | 15 | Sprint 235 | 0 | 3 | 5 | 0 | 4
Sprint 236 | 93 | 2 | 158 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | Sprint 236 | 4475 | 2 | 34 | 1 | 372 | 0 | 0 | 0 | 0 | 3 | Sprint 236 | 1 | 3 | 4 | 0 | 3
Sprint 237 | 250 | 8 | 2 | 0 | 12 | 0 | 5 | 2 | 1 | 0 | Sprint 237 | 4068 | 636 | 2 | 2 | 264 | 0 | 0 | 11 | 14 | 0 | Sprint 237 | 1 | 3 | 14 | 1 | 4
Sprint 238 | 189 | 2 | 0 | 0 | 7 | 0 | 2 | 0 | 0 | 0 | Sprint 238 | 4941 | 0 | 4 | 0 | 105 | 0 | 0 | 12 | 0 | 23 | Sprint 238 | 1 | 4 | 11 | 0 | 4
Sprint 239 | 36 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Sprint 239 | 4838 | 1 | 28 | 1 | 185 | 0 | 0 | 6 | 0 | 0 | Sprint 239 | 0 | 0 | 2 | 0 | 2
Sprint 240 | 110 | 2 | 18 | 0 | 11 | 0 | 2 | 2 | 0 | 0 | Sprint 240 | 5205 | 0 | 0 | 0 | 22 | 0 | 0 | 13 | 0 | 59 | Sprint 240 | 0 | 8 | 15 | 2 | 1
Sprint 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint 241 | 0 | 0 | 0 | 0 | 0
Sprint 245 | 118 | 0 | 11 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | Sprint 245 | 5573 | 0 | 13 | 1 | 193 | 0 | 0 | 0 | 0 | 0 | Sprint 245 | 0 | 0 | 2 | 0 | 1
Sprint 246 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint 246 | 5510 | 0 | 15 | 1 | 235 | 0 | 0 | 7 | 0 | 12 | Sprint 246 | 0 | 0 | 5 | 1 | 0

## closed by dev
Team | Corsair - Karate/Cypress tests | N/A | Sprint 223 | Sprint 227 | Sprint 234 | Sprint 237 | Sprint 238 | Sprint 239 | Sprint 240 | Sprint 241 | Sprint 242 | Sprint 243 | Sprint 244 | Sprint 245 | Sprint 247
Citation | [9 empty] | 8 | 3 | 1 | 1
Corsair | 15 | [7 empty] | 1 | 9 | 15 | 2 | 2
Firebird |  | 1 |  | 1 | 1 | 2 | 2 |  | 11 | 6 | 8 | 9 |  | 5
Folijet | [9 empty] | 3 | 5 | 2
Promin | [14 empty] | 1
Spitfire |  |  |  | 2 |  |  | 10 |  | 2 | 23 | 11 | 1 | 7 | 3
Thunderjet |  |  | 5 |  |  |  |  | 9 | 4 | 15 | 15 | 9 | 8 | 3
Vega | [6 empty] | 1 | 2 |  | 8 |  | 6 | 8 | 2
Volaris | [6 empty] | 2 |  | 4 | 8 | 7 | 10 |  | 1
Total | 15 | 1 | 5 | 3 | 1 | 2 | 15 | 11 | 22 | 80 | 64 | 40 | 26 | 14 | 1

## QA scope
Active sprint | Sprint 246
Team | Active Sprint | QA Effort | Tickets
Thunderjet | Sprint 246 | 21 | 35
Promin | Sprint 246 | 14 | 49
Vega | Sprint 246 | 13 | 24
Eureka | Sprint 246 | 12 | 31
Athena | Sprint 246 | 5 | 20
Spitfire | Sprint 246 | 2 | 13

## Release runs
Id | Name | Link | Total | passed | blocked | retest | failed | untested | unassigned | claimed | deferred | deferredHot | Defects | Description
3601 | [LOC] TLS: R1 2026 Trillium Bugfest testing | https://foliotest.testrail.io/index.php?/plans/view/3601 | 13436 | 11408 | 12 | 6 | 79 | 463 | 702 | 140 | 121 | 0 | MODROLESKC-424¦P1;MODINV-1400¦P2;STCOR-1088¦P2;UIIN-3686¦P2;BF-1517¦P3;EUREKA-878¦P3;MDEXP-925¦P3;MODKBEKBJ-842¦P3;MODROLESKC-416¦P3;MODSOURCE-944¦P3;MSEARCH-1263¦P3;UIREQMED-122¦P3;MODQM-513¦P4;UIREC-508¦P4;ERM-4135¦TBD;MODDICONV-417¦TBD;MODORDERS-1473¦TBD;MODREQMED-235¦TBD | <p data-pasted="true"><strong>List of reported open issues</strong><strong>:</strong></p><p><a href="https://folio-org.atlassian.net/issues?jql=created%20%3E%3D%20%222026-07-06%22%0Aand%20issuetype%20%3D%20Bug%0Aand%20created%20%3C%3D%20%222026-08-08%22%0Aand%20labels%20%3D%20TrilliumBF%0Aand%20status%20!%3D%20Closed%0AORDER%20BY%20created%20DESC%2C%20priority%20DESC">https://folio-org.atlassian.net/issues</a></p><p data-path-to-node="3" data-pasted="true"><strong data-start="117" data-end="130">Option 3:</strong> Targeted Smart Regression (~3 weeks)</p><p data-start="128" data-end="359">This option is designed to fit the available timeline while maintaining confidence in the quality of the release. It covers approximately <strong data-start="266" data-end="304">60% of the manual regression scope</strong> by prioritizing business-critical and high-risk areas.</p><p data-start="361" data-end="380"><strong data-start="361" data-end="380">Scope includes:</strong></p><ul data-start="381" data-end="703"><li data-section-id="ucezg0" data-start="381" data-end="415">Full LOC functionality coverage.</li><li data-section-id="tpk176" data-start="416" data-end="450">Complete Trillium release scope.</li><li data-section-id="1r58bmf" data-start="451" data-end="499">All high-risk and historically unstable areas.</li><li data-section-id="1s8l8l" data-start="500" data-end="580">Combined <strong data-start="511" data-end="528">ECS + Non-ECS</strong> execution (ECS environments are the primary focus).</li><li data-section-id="1jo4lek" data-start="581" data-end="703">Single-Tenant configuration validation through full automated regression, manual smoke testing, and exploratory testing.</li></ul><p data-start="705" data-end="728"><strong data-start="705" data-end="728">Scope optimization:</strong></p><ul data-start="729" data-end="969"><li data-section-id="z5slyu" data-start="729" data-end="762">Exclude low-priority scenarios.</li><li data-section-id="1tgc443" data-start="763" data-end="814">Exclude stable tests with no history of failures.</li><li data-section-id="1hyfd3n" data-start="815" data-end="890">Remove approximately <strong data-start="838" data-end="868">80% of the Community scope</strong> (Extended and above).</li><li data-section-id="nzih8l" data-start="891" data-end="969">Exclude low-risk areas</li></ul>
3682 | R1 2025 Sunflower Critical Service Patch #9 | https://foliotest.testrail.io/index.php?/plans/view/3682 | 4457 | 0 | 0 | 0 | 0 | 4437 | 0 | 20 | 0 | 0
3688 | TLS: R1 2025 Sunflower Critical Service Patch #9 | https://foliotest.testrail.io/index.php?/plans/view/3688 | 4439 | 303 | 0 | 0 | 19 | 4097 | 0 | 20 | 0 | 0

## CI status
dashboard | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67
Group | GroupLink | Name | Number | Url | Total | Passed | Failed | Skipped | productBug | automationBug | systemIssue | noDefect | toInvestigate | Bugs
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1391 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9670 | 293 | 289 | 4 | 0 | 2 | 1 | 0 | 0 | 1 | UILD-842¦https://folio-org.atlassian.net/browse/UILD-842
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1390 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9664 | 226 | 218 | 8 | 0 | 2 | 3 | 0 | 0 | 1
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1389 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9663 | 292 | 284 | 8 | 0 | 2 | 4 | 0 | 0 | 3
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1388 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9661 | 293 | 288 | 5 | 0 | 2 | 3 | 0 | 0 | 0
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1387 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9660 | 293 | 287 | 6 | 0 | 3 | 3 | 0 | 0 | 0
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1386 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9657 | 293 | 289 | 4 | 0 | 2 | 2 | 0 | 0 | 0
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1385 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9656 | 293 | 288 | 5 | 0 | 2 | 2 | 0 | 0 | 1
Quality Gates | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/67 | folioQualityGates | 1384 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9653 | 293 | 289 | 4 | 0 | 2 | 2 | 0 | 0 | 0
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 350 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9654 | 3959 | 3780 | 179 | 0 | 12 | 23 | 0 | 0 | 161 | UILD-842¦https://folio-org.atlassian.net/browse/UILD-842;FAT-27417¦https://folio-org.atlassian.net/browse/FAT-27417;MODKBEKBJ-844¦https://folio-org.atlassian.net/browse/MODKBEKBJ-844;MODKBEKBJ-841¦https://folio-org.atlassian.net/browse/MODKBEKBJ-841;MODSOURMAN-1363¦https://folio-org.atlassian.net/browse/MODSOURMAN-1363;MODQM-513¦https://folio-org.atlassian.net/browse/MODQM-513
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 349 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9641 | 3956 | 3743 | 213 | 0 | 17 | 98 | 1 | 0 | 127
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 348 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9628 | 4896 | 4716 | 180 | 0 | 17 | 31 | 0 | 0 | 175
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 347 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9616 | 4896 | 4673 | 223 | 0 | 23 | 43 | 0 | 0 | 195
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 346 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9604 | 4749 | 4515 | 234 | 0 | 1 | 55 | 0 | 0 | 215
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 345 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9594 | 4523 | 4021 | 502 | 0 | 3 | 94 | 0 | 0 | 478
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 344 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9583 | 3448 | 2921 | 527 | 0 | 0 | 120 | 1 | 0 | 641
Nightly Runs | https://report-portal.ci.folio.org/ui/#cypress-nightly/dashboard/45 | runNightlyCypressEurekaTests | 343 | https://report-portal.ci.folio.org/ui/#cypress-nightly/launches/all/9572 | 2382 | 2097 | 285 | 0 | 1 | 51 | 0 | 0 | 265

## Coverage by type
as of 24.07
Group | Cypress | Karate | Backend Component | Manual
Smoke | 441 | 11 | 10 | 108
Critical Path | 2226 | 110 | 61 | 1034
Extended | 3155 | 87 | 105 | 2408
Backend | 6 | 6 | 0 | 41
Edge Cases | 37 | 1 | 1 | 307
Total | 5865 | 215 | 177 | 3898

## Bug status latest
Sprint | Status | Count
Sprint 246 | Blocked | 2
Sprint 246 | In Refinement | 2
Sprint 246 | Open | 2

## Defect impact
Scanned runs | 56
Defect | Priority | Unique tests | Runs seen
EUREKA-536 | P3 | 69 | 11
UIIN-3686 | P2 | 28 | 1
UILDP-196 | P3 | 8 | 1
MODINVOICE-659 | TBD | 5 | 1
UIIN-3470 | P3 | 4 | 1
UIEH-1452 | P3 | 3 | 1
MODSOURMAN-1218 | P4 | 2 | 9
BF-1480 | P3 | 2 | 3
UIIN-3520 | P3 | 2 | 3
UIU-3606 | P4 | 2 | 2
EUREKA-878 | P3 | 2 | 1
MODELINKS-426 | P3 | 2 | 1
MODROLESKC-424 | P1 | 2 | 1
MODSOURMAN-1445 | TBD | 1 | 4
UIPQB-291 | P3 | 1 | 4
MODQM-513 | P4 | 1 | 3
MODSOURMAN-1363 | P3 | 1 | 3
MODROLESKC-416 | P3 | 1 | 2
BF-1517 | P3 | 1 | 1
ERM-4135 | TBD | 1 | 1
EUREKA-668 | P3 | 1 | 1
EUREKA-863 | P3 | 1 | 1
FAT-27003 | P3 | 1 | 1
MDEXP-917 | P3 | 1 | 1
MDEXP-925 | P3 | 1 | 1
MODDICONV-417 | TBD | 1 | 1
MODFIN-260 | P3 | 1 | 1
MODINV-1317 | P2 | 1 | 1
MODINV-1400 | P2 | 1 | 1
MODINVSTOR-1532 | P3 | 1 | 1
MODKBEKBJ-842 | P3 | 1 | 1
MODORDERS-1473 | TBD | 1 | 1
MODREQMED-235 | P3 | 1 | 1
MODSOURCE-775 | P3 | 1 | 1
MODSOURCE-944 | P3 | 1 | 1
MSEARCH-1263 | P3 | 1 | 1
STCOR-1088 | P2 | 1 | 1
UIIN-3526 | P4 | 1 | 1
UIOR-1541 | P4 | 1 | 1
UIPFO-57 | P4 | 1 | 1
UIREC-508 | P4 | 1 | 1
UIREQMED-122 | P3 | 1 | 1
UIROLES-179 | P3 | 1 | 1

## Area coverage
as of 08.07
Area | Automated | Manual | Coverage %
Acquisition Units | 33 | 3 | 91.7
Agreements | 18 | 145 | 11
API- MARC SRS query | 0 | 3 | 0
Bulk Edit | 625 | 75 | 89.3
Bursar | 0 | 2 | 0
Calendar | 1 | 1 | 50
Check in | 16 | 6 | 72.7
Check out | 14 | 16 | 46.7
Circulation | 15 | 8 | 65.2
Circulation log | 65 | 17 | 79.3
Citation | 215 | 141 | 60.4
Claiming | 3 | 8 | 27.3
Consortia | 162 | 202 | 44.5
Consortia Vega | 12 | 49 | 19.7
Course Reserves | 1 | 0 | 100
Dashboard | 0 | 22 | 0
Data Export | 208 | 46 | 81.9
Data Import | 382 | 417 | 47.8
DCB | 10 | 31 | 24.4
eHoldings | 107 | 62 | 63.3
Eureka | 159 | 38 | 80.7
Export Manager | 36 | 33 | 52.2
Fees&Fines | 103 | 147 | 41.2
Finance | 165 | 63 | 72.4
General | 0 | 3 | 0
GOBI integration | 4 | 13 | 23.5
INN-Reach Integration | 0 | 121 | 0
Inventory | 1150 | 373 | 75.5
Invoices | 129 | 123 | 51.2
License | 2 | 86 | 2.3
Lists | 288 | 100 | 74.2
Loans | 30 | 37 | 44.8
MARC | 1325 | 239 | 84.7
Mediated requests | 0 | 96 | 0
Mosaic integration | 0 | 10 | 0
Notes | 20 | 0 | 100
OAI-PMH | 197 | 75 | 72.4
Obsolete | 2 | 4 | 33.3
Orchid | 3 | 0 | 100
Orders | 274 | 407 | 40.2
Organizations | 76 | 12 | 86.4
Patron notices | 26 | 29 | 47.3
Permissions | 50 | 92 | 35.2
Poppy | 4 | 0 | 100
Quesnelia | 2 | 0 | 100
Ramsons | 0 | 1 | 0
Reading Room Access | 10 | 32 | 23.8
Receiving | 15 | 222 | 6.3
Remote Storage | 15 | 4 | 78.9
Reporting | 0 | 8 | 0
Request slips printing | 1 | 14 | 6.7
Requests | 41 | 119 | 25.6
Serials Management | 0 | 18 | 0
Settings | 4 | 8 | 33.3
Settings (General) | 4 | 2 | 66.7
SIP2 Integration | 0 | 5 | 0
Staff slips | 15 | 28 | 34.9
Sunflower | 2 | 1 | 66.7
Tags | 4 | 1 | 80
Tenant | 21 | 8 | 72.4
test_ai | 0 | 6 | 0
Title Level Request | 53 | 31 | 63.1
Users | 70 | 108 | 39.3
Total | 6187 | 3971 | 60.9

## QA debt
Team | QA Effort
Thunderjet | 10
Vega | 4.5
Promin | 3
Corsair | 3
Athena | 0.5
Firebird | 0.5
Volaris | 0.5

## QA scope EBSCO
Team | Score | Project
Helios | 2 | HELIOS

## QA debt EBSCO
Team | Story Points | Project